TAIR GO Progress Report, December 2007

1. Staff

GO funded GO annotation (1.4 FTE):

Tanya Berardini: 0.4 FTE

Donghui Li:  1 FTE

Non-GO funded GO annotation (0.45 FTE):

Peifen Zhang: 0.10 FTE (January - June 2007)

Christophe Tissier: 0.35 FTE (January - August 2007)

Hartmut Foerster: 0.25 FTE (January - August 2007)

GO funded Software Support Staff (0.03 FTE):

Joe Filla: 0.05 FTE (Jan 2007)

Larry Ploetz: 0.03 FTE (Mar - Dec. 2007)

Non-GO funded Software Support Staff (0.4 FTE):

Bob Muller: 0.4 FTE (Jan - Dec 2007)

2. Annotation Progress

Based on Arabidopsis genome release TAIR7 (4/07)

Protein coding genes:   27,029

Pre-tRNA genes:              689

rRNA genes:                      15

snRNA genes:                    13

snoRNA genes:                  71

miRNA genes:                  114

other RNA genes:             221

pseudogenes:                 3,889

Total:                           32,041 (without pseudogenes: 28,152)

Genetic loci:                     796

Table 1: Number of Annotations to Various GO Aspects

| ANNOTATIONS | Process |  |  | Function |  | Component |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Dec. 2006 | Dec. 2007 | change | Dec. 2006 | Dec. 2007 | change | Dec. 2006 | Dec. 2007 | change |
| non-IEA/non-ND | 9582 | 11038 | +1456 | 8492 | 9048 | +556 | 5014 | 5976 | +962 |
| IEA | 5834 | 6627 | +793 | 3047 | 5062 | +2015 | 13876 | 10334 | -3542 |
| ND | 9490 | 9062 | -428 | 2768 | 2453 | -315 | 9053 | 8693 | -360 |

Table 2: Number of Genes Annotated to Various GO Aspects

| GENES | Process |  |  | Function |  |  | Component |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Dec. 2006 | Dec. 2007 | change | Dec. 2006 | Dec.2007 | change | Dec. 2006 | Dec.2007 | change |
| non-IEA/non-ND | 5481 | 5897 | +416 | 6034 | 6247 | +213 | 3254 | 3787 | +533 |
| IEA | 4067 | 4516 | +449 | 4067 | 2833 | -1234 | 11239 | 8085 | -3154 |
| ND | 8760 | 8368 | -392 | 2584 | 2286 | -298 | 8403 | 8080 | -323 |

3. Methods and strategies for annotation

(please note % effort on literature curation vs. computational annotation methods)

a.  Literature curation: We curate on a paper by paper basis.  In addition to GO-related information, we also 	capture expression patterns using the PO vocabularies, allele, germplasm and phenotype information. 	(95% effort)

b.  Computational annotation strategies: We perform two types of computational analyses for GO annotation 	purposes:  INTERPRO domain mapping/INTERPRO2GO and TargetP analysis. Annotations are 	updated when the INTERPRO2GO mapping file changes or when the genome annotation changes. (5% 	effort)

c.  Priorities for annotation:

We focus on extracting information from the most recently published literature.  Because of the large 	number of papers that come out every month, we have a triage procedure that assigns a priority (high, 	medium, normal) to a paper based on the journal in which it is published.  Our current aim is to have 	complete coverage of the high priority papers and work on the other two categories as time allows.

Our high priority journals are:

| PNAS | Science |
| --- | --- |
| The EMBO Journal | The Plant Cell |
| The Plant Journal | PLoS Biology |
| Trends in Plant Sciences | Cell |
| Current Biology | Development |
| Genes and Development | Nature |
| Nature Cell Biology | Nature Genetics |
| Nucleic Acids Research |  |

4. Presentations and Publications

a. Papers with substantial GO content

none

b. Presentations including Talks and Tutorials and Teaching

1.  PAG (Plant and Animal Genome) Meeting, San Diego, CA, January 2007

Donghui Li presented one workshop on GO and annotation of the Arabidopsis genome using GO.

2. 18th International Conference on Arabidopsis Research, Beijing, China, June 2007 
            Donghui Li presented one workshop on GO and annotation of the Arabidopsis genome using GO.

3. ASPB (American Society for Plant Biologists) Meeting, Chicago, IL, July 2007

Tanya Berardini presented one workshop which focused on GO and its applications for plant 	research. 

	4. Plant Physiology Editorial Board meeting, Chicago, IL, July 2007
	Tanya Berardini gave a 15 minute presentation to request the journal's collaboration in obtaining GO-	like annotations from submitting authors.  The idea is to ask for the author's words to describe the 	function/process/component/expression pattern of their gene/s and curators at TAIR will map that to 	existing GO and PO (Plant Ontology) terms. The presentation was well received and a submission 	process is under development and is anticipated to be put into place by the first quarter 2008.  If the 	initial implementation goes well, TAIR will probably develop more automated ways to incorporate 	the incoming data as the current process is quite labor-intensive and manual.
 
	5.  2nd International Biocuration Meeting, San Jose, CA, October 2007
	Tanya Berardini gave a talk during the Collaboration Between Journal Publishers and Database 	Curators workshop on the impending collaboration between TAIR and the journal Plant Physiology 	with respect to collection of GO-like annotations.  The talk generated a lot of interest and discussion 	among the workshop's attendees.  Many MODs are interested in how this experiment will play out.

c. Poster presentations

none

5. Other Highlights:

a. Ontology Development Contributions:

1.  Tanya Berardini has been involved in developing two areas of the process ontology:  cell wall 	metabolism with the help of postdocs in Chris Somerville's lab (Carnegie Institution, Dept. of Plant 	Biology) and stomatal development with the help of Dominique Bergmann (Stanford University, Dept. 	of Biology).
	2.  Donghui Li has been responsible for the addition of new GO terms requested by TAIR curators.
	3. Both Tanya and Donghui worked closely with Jennifer Deegan from the GO Editorial Office to 	resolve outstanding plant-related terms in the 'sensu' revamp project.  Areas that received particular 	attention were male and female gametophyte development, gametogenesis, and pollination.
	4. Tanya and Jennifer were involved in sorting out meiotic spindle formation and enlisted the help of a 	spindle assembly expert referred by Dictybase, Dr. Ralph Gräf (Universität Potsdam, Germany).

5.   Tanya has been working with David Hill from MGI on resolving outstanding ontology issues that 	need to be fixed before the new 'regulates' relationship can be implemented. 
	6.  As a result of ontology development for various projects described above, a total of 153 terms have 	been added to GO in the TAIR number range.  The dates for these additions span from Dec. 7, 2006 to 	Nov. 30, 2007.

b. Annotation Outreach and User Advocacy Efforts:

1. Tanya Berardini and Donghui Li have organized three workshops which focused on GO and its 	applications for plant research.  Please refer to Presentations and Publications section for details.

2. Tanya and Donghui have been working closely with other members of the TAIR curator team on 	getting users to submit functional annotations using GO.  An intuitive simple-to-use submission form is 	available to download from TAIR website 	http://www.arabidopsis.org/submit/functional_annotation.submission.jsp).  It is estimated that about 1% 	of the GO annotations at TAIR were submitted by users (about 1,000 annotations).

c. Other Highlights:

1. Tanya is a member of the OBO-Edit working group.

2. Donghui is a member of the AmiGO working group.