WormBase GO Progress Report, Fall 2004

WormBase Progress Report

Gene Ontology Consortium Meeting, October 15 and 16, 2004

  - WormBase-GO Staff

Literature Curation: Carol Bastiani, Ranjana Kishore, Kimberly

Van Auken (Caltech)

RNAi2GO Mappings: Erich Schwarz (Caltech)

Anatomy2GO: Raymond Lee (Caltech)

Interpro2GO: Darin Blasiar (Wash U), Sanger Center

Software Development: Juancarlos Chan, Igor Antoshechkin (Caltech)

Principal Investigator (Caltech): Paul Sternberg

Literature curators devote ~50% of their time to GO curation, while

others devote varying amounts, but generally < 50%.

2a. Annotation Progress

As of October 12, 2004:

Current     Previous      Added     % Increase

(1/13/04)

Total Annotations            23,385        14,043          9,342             83%

IEA  Annotations            18,258        11,403          6,855               80%

non-IEA Annotations               5,127           2,640          2,487               97%

Total Gene Products            11,645            6,959         4,686               84%

non-IEA (approx.)              1,200               900             300               67%

Biological Process               8,992            5,153         3,839              85%

non-IEA                3,929            1,611                                120%

Molecular Function               9,314            5,793          3,521              80%

non-IEA                     424            332                                    64%

Cellular component                 5,079           3,097        1,982              82%

non-IEA                     774               697               77            55%

Total References                    610               358            252              85%

- Methods of Annotation

a.  In terms of time, literature curation is our main focus.   Annotations

are derived almost exclusively from the primary literature, with few

annotations taken from review articles.  Remaining annotations are

derived from meeting abstracts, which are readily accessible on the

WormBase web site.

b.  We employ two automated mappings: RNAi2go and Interpro2go.

RNAi2GO (IMP)

The RNAi2go mappings are applied to RNAi screens and map

resulting phenotypes to GO terms.  For example, an RNAi phenotype

of Emb (embryonic lethal) is automatically mapped to the GO

Biological Process term GO:0009792 embryonic development (sensu

Metazoa).  These mappings appear on each of the relevant gene pages

and are continuously updated as new results are reported in the

literature.

Interpro2GO (IEA)

For our gene association file, we are submitting Interpro2GO mappings

in accordance with every “frozen” release of WormBase.  To aid in

data analysis, WormBase releases a frozen version of the database

every tenth release, or approximately every five months.  For each

frozen release we will include a new set of Interpro2GO mappings

with our gene association file.

c.  Our quality control measures include a number of checking scripts to

ensure that our gene association file is formatted properly, that obsolete

GO terms are promptly replaced, and that gene and protein identifiers

are kept up-to-date, since sequence curation is ongoing and gene

models do still change.  We also plan to move towards automated

uploads of  our gene association file, so that daily updates will now be

available to our users.

4.  Ontology Development

WormBase contributions to ontology development have generally

been in the areas of embryonic and larval development, with some

additional contributions in neurobiology and cellular components

involved in intraflagellar transport.

Terms Added or Definitions Modified for:

axonemal heterotrimeric kinesin-II complex

mesectoderm development

mesendoderm development

intraflagellar transport particle

intraflagellar transport particle complex A

intraflagellar transport particle complex B

oogenesis

P granule

polar granule

pole plasm

synaptic transmission, glutamatergic

Pending:

cell soma

induction

lateral inhibition

5.  WormBase Publication Highlighting use of Gene Ontology:

Schwarz, E.M. and Sternberg, P.W. (2004). Searching WormBase for

information about Caenorhabditis elegans. Current Protocols in

Bioinformatics, 1.8.1-1.8.44.

Muller HM, Kenny, EE, Sternberg, PW

Textpresso: An Ontology-Based Information Retrieval and Extraction

System for Biological Literature

PloS Biol. 2004 Sep 21;2(11):E309

PMID: 15383839

Abstract:

We have developed Textpresso, a new text-mining system for scientific literature  whose capabilities go far beyond those of a simple keyword search engine. Textpresso's two major elements are a collection of the full text of scientific articles split into individual sentences, and the implementation of categories of terms for which a database of articles and individual sentences can be searched. The categories are classes of biological concepts (e.g., gene, allele, cell or cell group, phenotype, etc.) and classes that relate two objects (e.g., association, regulation, etc.) or describe one (e.g., biological process, etc.). Together they form a catalog of types of objects and concepts called an ontology. After this ontology is populated with terms, the whole corpus of articles and abstracts is marked up to identify terms of these categories. The current ontology comprises 33 categories of terms. A search engine enables the user to search for one or a combination of these tags and/or keywords within a sentence or document, and as the ontology allows word meaning to be queried, it is possible to formulate semantic queries. Full text access increases recall of biological data types from 45% to 95%. Extraction of particular biological facts, such as gene-gene interactions, can be accelerated significantly by ontologies, with Textpresso automatically performing nearly as well as expert curators to identify sentences; in searches for two uniquely named genes and an interaction term, the ontology confers a 3-fold increase of search efficiency. Textpresso currently focuses on Caenorhabditis elegans literature, with 3,800 full text articles and 16,000 abstracts. The lexicon of the ontology contains 14,500 entries, each of which includes all versions of a specific word or phrase, and it includes all categories of the Gene Ontology database. Textpresso is a useful curation tool, as well as search engine for researchers, and can readily be extended to other organism-specific corpora of text. Textpresso can be accessed at http://www.textpresso.org or via WormBase at http://www.wormbase.org.

6.  Highlights/Future Plans

GO Expression Search Tool

Using the microarray analysis performed by Stuart et. al., Science.

2003 Oct 10;302(5643):249-55, Igor Antoshechkin has developed a tool

that allows WormBase  curators to query GO annotations made to

orthologous and co-expressed genes from C. elegans, Drosophila,

S. cerevisiae, and humans.  This tool is very useful for checking the

completeness of our annotations and ensuring that there is

consistency between WormBase GO annotations and those of other

model organism databases.  The tool is available at:

http://elbrus.caltech.edu/cgi-bin/igor/go_express.cgi

README File

As per discussion at the GO Annotation Camp, we will now be

routinely submitting a README file that explains the types of

annotations in our gene association file, our curation approach,

and where to go for questions or additional information about

GO annotations in WormBase.

Database Identifiers

In the past, WormBase only had unique database identifiers for

transcripts and proteins.  With the introduction of a new gene

model this past summer, we now have unique identifiers for every

gene, as well.  Thus, we are now able to accurately assign the

the object type to which an annotation is made, for every annotation.

Since most of our previous annotations were attributed to proteins,

we are in the process of retrofitting our gene association file to

assign annotations to genes wherever appropriate.

Anatomy Ontology and GO Terms

Raymond Lee has developed an anatomy ontology for WormBase.

(Lee RYN, Sternberg PW. Building a cell and anatomy ontology of

Caenorhabditis elegans. Comparative and Functional Genomics

4: 121-126 2003.)  He is now in the process of assigning GO terms

to cells.  For example, the hermaphrodite-specific neuron (HSN) that is

essential for egg-laying will be annotated to the Biological Process

term, GO: 0018991, oviposition.  This will allow us to link the C. elegans

anatomy to relevant biological processes.

WormBase Web Site Gene Ontology Display

One of our major goals for the upcoming year is to overhaul the display

of the Gene Ontology annotations on each of the respective gene pages.

At present, we only display the annotation, the evidence code, and the

reference.  We would like to expand the display such that users would

see the annotations, but then be able to link to a table displaying all

relevant information, including  evidence codes, references, object type

to which the annotation was made, interacting genes or proteins for IGI

and IPI annotations, Uniprot accessions for ISS annotations, etc.  We

believe this will allow WormBase users to perform much more thorough

analysis of our GO annotations.